## Sheet1
# | Enhancements | Module | Assigning to | Status | Remark
1 | Project/WBS/Assignment creation in easy way..may be tree | Setting |  | Not Started
2 | Add effort in project grid in project master and remove project type & last updated | Setting | Mayur | Completed
3 | No Scroll in document upload in Document system | Document |  | Completed
4 | No Scroll in Bug creation | Bug |  | Completed
5 | Add filter on top of each column in view bug screen | Bug | Jay | Completed
6 | Add camera feature to take screenshot and attach to Bug/Alternatively copy paste of image from Snip | Bug |  | Not Started
7 | Inactive employee not to be shown in any transaction screen. Timesheet table shows all employee | All |  | Completed
8 | Asset Admin access to be given to some person | Asset |  | Completed
9 | Text search in document not working properly | Document |  | Completed
10 | Timesheet scroll not proper | Timesheet |  | Completed
11 | Project Summary extra columns requried | Project | Mayur | Completed | Column Added : Project Name,Project Manager,Account Head,Pl. Total Effort,Pl. Start DatePl., End DatePl. Act., Start Date,Pl. Act. End, DateAct. End Date,Expected Comp.,Actual Comp.,Total Hrs Booked,Compl. Based On hrs Booked,Open Bugs,Closed Bugs,
12 | Project plan "Actual End date" will be filled automately when the task is marked 100% complete | Project |  | Completed
13 | User master should have user name in the header | Setting |  | Completed
14 | Remove all alerts and add the status on the page such as "Submitted" | All |  | Partialy completed
15 | Find a way to assign modules to multiple users in easy way | Setting |  | Not Started
16 | Show number of downloads and ratings in my uplaods | Document |  | Completed
17 | Menu Fonts in White | All |  | Completed
18 | Theme Implementation | All |  | Not Started
19 | Notifications for all Modules | All |  | Completed
20 | Resource View to have resource total effort by project and all project together | Project |  | Not Started
21 | Resource View to also show gant chart for resource tasks | Project |  | Not Started
22 | Option to adjust column width in project Plan | Project |  | Completed
23 | Color Code with Red the tasks which are delayed as per Planned actual End Date | Project |  | Completed
24 | Create Report as per explained to Hardik | All |  | Not Started
25 | Option to show and hide columns in Project and Bug | Project & Bug | Mayur & Jay | Partialy completed
26 | Quick Interview Schedule option | RMS |  | Not Started
27 | Option to add comments by the tasks owner in their tasks | Project |  | Completed
28 | Option for Project and above to see the comments | Project |  | Completed
29 | First time users to be taken to change password screen first | All |  | Completed
30 | Add a disclaimer in the mail notification | All | Jay | Completed
31 | Add a Caldendar view of tasks | Project |  | Not Started
32 | Gantt Chart for Tasks | Project |  | Not Started
33 | In future, it will be for all expect public domain, such as yahoo, gmail, outlook, Hotmail, and any other that you can add | All | Ashish | Completed
34 | All mails notification will happen from the domain that the admin has registered from. So 1st page after registration and login will be setting up email config. | All | Ashish | Completed
35 | Client contact person will act as user for Bug system if allowed by the Admin and email will go for activation from the Admin domain only. | Setting |  | Completed
36 | System will count the number of free days remaining and will show at the top. System will not allow for login beyond the free days | All | Ashish | Completed
37 | Login detail capture in a table | All | Avinash | Completed
38 | Super Admin, login control i.e super Admin can see which companies are registered with registered user login details. Super Admin can stop a company to login and all users in that company will be prohibited to login | All | Avinash | WIP
39 | Excel download and uploads | All |  | Completed
40 | Multiple login not allowed from the same user from different device | All | Jay | Not Started
41 | Adding free and paid logic. Will make a module paid and if user select the module then a payment page will appear | All | Ashish | Not Started
42 | Adding a payment gateway- one page checkout will be there | All | Ashish | Not Started
43 | Adding content to the main website and other pages in the website | All |  | Completed
44 | Offer Letter Generation from RMS system | RMS |  | Not Started
45 | Offer letter approval | RMS |  | Not Started
46 | Offer letter auto mail post approval to candidate | RMS |  | Not Started
47 | background verification document upload | RMS |  | Not Started
48 | TP access for background verification | RMS |  | Not Started
49 | TP update on background verification | RMS |  | Not Started
50 | HR view of BV | RMS |  | Not Started
51 | API integration for job posting to Naukri and Linkedln | RMS |  | Not Started
52 | Internal Job Postings | RMS |  | Not Started
53 | Internal Employees access for applying to internal Job postings | RMS |  | Not Started
54 | HR view of internal job postings and applications | RMS |  | Not Started
55 | Employee filling and uplaoding referral resumes via portal | RMS |  | Not Started
56 | Add filter to all values in Project plan | Project |  | Completed
57 | Provide access to a plan ( display) to any resource | Project | Mayur | Completed
58 | Resource View Gantt chart and also effort table | Project | Mayur | WIP
59 | filters for dates | Project |  | Completed
60 | Do not show save and Submit until something is changed in the plan. Show it as soon as something is changed | Project |  | Completed
61 | Are you send mail confirmation for plan rejection or approval | Project | Mayur | Completed
62 | Color code for tasks which are past due | Project |  | Completed
63 | Color code for tasks which are due today | Project |  | Completed
64 | A filter at the top to show Past Due, Due Today, Due Tom, Due in 7 days..this will be multi select | Project |  | Completed
65 | When I make the column smaller then automatically wrap the text if there is not enough space | Project | Mayur | Completed
66 | By Default Load the latest Version of Plan | Project |  | Completed
67 | If a Plan is submitted for Approval and not approved/rejected, then a auto mail will go every day to Manager and his supervisor until the plan is approved/rejected | Project | Jay | WIP
68 | Once a Plan is approved, then deletion of tasks should be shown as striked off | Project | Mayur | Completed
69 | Once a plan is approved any changed to it in the next version will be highligted via som color or font style | Project | Mayur | WIP
70 | A Icon at the top to export the plan in excel | Project |  | Completed
71 | A Icon at the top to print the plan | Project |  | Rejected
72 | A icon at the top to email the plan in excel format | Project | Mayur | Completed
73 | A Icon + and - to collapse and Expand all | Project |  | Completed
75 | If any employee is a supervisor then timesheet role is automatically as supervisor. No need to select the drop down | Setting | Avinash | Completed
76 | Find a way to edit employee in easy way | Setting | Avinash | Completed
77 | Provide a search option in Edit employee screen. | Setting |  | Not Started
78 | Provide a Back option in Edit screens, when user clicks on back user is taken to grid on the same page as he was | Setting | Jay | Completed
79 | Mail SMTP settings | Setting |  | Completed
80 | For other clients, first screen after change pwd is Mail settings | Setting |  | Completed
81 | Option for Test mail | Setting | Ashish | Completed
82 | Integrate Thumb data in timesheet | Timesheet |  | Completed
83 | Show timesheet table in others data according to historical records. I.e show only those emp who were present in that fornight | Timesheet | Avinash | Completed
84 | Similary do not show inactive employee from the next fortnight they become inactive. | Timesheet | Avinash | Completed
85 | Zipped File not searched in content search | Document |  | Completed
86 | Load a file and then immediately click on other module, File does not load | Document | Avinash | Completed
87 | in History, for a round latest status should be shown in Interview schedule history section | RMS |  | Completed
88 | there should be a Icon to show comments from the interviewer in the history section | RMS |  | Not Started
89 | A mail/meeting Invite should go to interviewer with Candidate resume, interview Date and time | RMS |  | Not Started
90 | in Interview Feedback page, we have to build section for feedback such as Functional feedback, technical feedback as per form shared by Amit | RMS |  | Not Started
91 | Holiday screen employee wise fortnight wise |  | Avinash | Not Started